## Group A_Technocrats_Document
Application | Module | Activity | Task | Start Date | End Date | Status | Remarks
Student Result Management System | Minutes Of Meeting(MOM) | Discussed about the requirements. | Prepared the MOM sheet. | 2021-09-17 | 2021-09-17 | Completed
Student Result Management System | WorkBreakdownStructure | Distributed the work. | Prepared the WBS sheet. | 2021-09-18 | 2021-09-18 | Completed
Student Result Management System | Sequence Diagrams | Discussed about the flow of all the Sequence Diagrams. | Created all the Sequence Diagrams. | 2021-09-19 | 2021-09-19 | Completed
Student Result Management System | Class Diagrams | Discussed about the flow of all the Class Diagrams. | Created all the Class Diagrams. | 2021-09-20 | 2021-09-20 | Completed
Student Result Management System | Activity Diagrams | Discussed about the flow of all the Activity Diagrams. | Created all the Activity Diagrams. | 2021-09-20 | 2021-09-20 | Completed
Student Result Management System | Enitity Relational Diagram | Discussed about the flow of all the Enitity Relational Diagrams. | Created all the Enitity Relational Diagrams. | 2021-09-21 | 2021-09-21 | Completed
Student Result Management System | Design Document | Discussed about the different queries. | Created the Design Document. | 2021-09-21 | 2021-09-21 | Completed
Student Result Management System | DataBase Design | Discussed about the different tables and stored procedures to be created. | Created DB Design | 2021-09-22 | 2021-09-23 | Completed
Student Result Management System | ScreenShots of Prototypes | Discussed about the flow of the project and the output screen | Created the forms. | 2021-09-24 | 2021-09-24 | Completed
Student Result Management System | Asp.Net Core Web API Design | Discussed about the flow of Coding Standard Document. | Created the ASP.NET Web API Design | 2021-09-26 | 2021-09-26 | Completed
Student Result Management System | Asp.Net Core MVC Design | Discussed about the flow of Coding Standard Document. | Created the ASP.NET Core MVC Design | 2021-09-27 | 2021-09-27 | Completed
Student Result Management System | Coding | Discussed about the flow. | Writing the code of Admin Module | 2021-09-29 | 2021-09-30 | Completed
Student Result Management System | Coding | Discussed about the flow. | Writing the code of Student Module | 2021-09-30 | 2021-10-01 | Completed
Student Result Management System | Coding | Discussed about the flow. | Writing the code of Semester Module | 2021-10-02 | 2021-10-02 | Completed
Student Result Management System | Coding | Discussed about the flow. | Writing the code of Branch Module | 2021-10-03 | 2021-10-03 | Completed
Student Result Management System | Coding | Discussed about the flow. | Writing the code of ResultModule | 2021-10-04 | 2021-10-04 | Completed
Student Result Management System | Coding | Discussed about the flow. | Writing the code of Course Module | 2021-10-05 | 2021-10-05 | Completed
Student Result Management System | UnitTestPlan(UTP) | Discussed about the Test cases. | Created the Unit Test Case Plan | 2021-10-06 | 2021-10-06 | Completed
Student Result Management System | Unit Testing | Gone through the Unit Test Plan. | Unit Testing. | 2021-10-07 | 2021-10-07 | Partially Completed